Executive Summary & Scope of Work

Project Title: IoT-Based Smart Wax Machine (DashCam-Grade Control Logic)

Client: Mella (April)

Submitted By: NetzOptimize

Date: 13/Nov/2025

1. Executive Summary

This proposal outlines the development plan, technical flow, and scope for creating a smart IoT-based Wax Heating Machine powered by the ESP32-C5 module, featuring Wi-Fi connectivity, OTA updates, temperature control, and mobile app integration.

The objective is to design and build a scalable and production-ready system, starting from a proof of concept (POC) and progressing toward custom PCB development (Logic Controller and Power Controller boards).

The final product will allow users to operate the Wax Machine both manually and through a mobile application, ensuring intelligent temperature regulation, safety, and seamless connectivity.

2. Project Flow Overview

The development will proceed through the following structured phases:

Phase 1: Proof of Concept (POC) Development

Objective:
Create a breadboard-based prototype using ESP32-C5, DS18B20 temperature sensor, LED indicators, knob control, and relay operation to simulate heater functionality.

Key Deliverables:

- Functional prototype demonstrating:

  - Wi-Fi provisioning (self-advertised SSID)

  - OTA firmware update

  - LED status (Configuration Mode, Connected, Heating, Threshold Reached)

  - Knob-based temperature control

  - DS18B20 temperature reading and relay activation logic

- Base firmware with OTA partitioning

Phase 2: Multi-Chip Validation

Objective:
Test firmware on multiple ESP32-C5 boards to ensure consistent functionality and compatibility across chip variants.

Key Deliverables:

- Multi-unit firmware testing report

- Stable and portable firmware build

- Identified improvements before PCB phase

Phase 3: Hardware Design (PCB Stage 1 & 2)

A. Logic Controller PCB

- ESP32-C5 module integration

- LED indicators (5V RGB)

- Knob interface (Analog/Digital Input)

- DS18B20 Thermostat interface

- Relay control output

- Programming and debug ports

- OTA-ready firmware flashing interface

B. Power Controller PCB (We will use the V2 InBuild PCB)

- 110V AC input

- Surge and overload protection (TVS, MOV)

- AC-to-DC 5V converter (isolated, regulated)

- Relay for heater load control

- Power and thermal safety provisions

Phase 4: Mobile Application Integration

Objective:
Design the mobile app workflow for user registration, product addition, Wi-Fi configuration, and control.

Flow:

- App Installation → Login:
User logs in using existing web credentials (Username & Password).
No database changes will be made; integration will use existing authentication APIs.

- Add Product:

  - Scan product QR Code / Enter unique ID.

  - Each product advertises its own Wi-Fi SSID (unique per device).

  - App connects to product’s temporary Wi-Fi and sends customer Wi-Fi credentials.

- Backend Verification: (We will not make any changes in the present logic)

  - Device connects to client’s cloud server.

  - Server checks subscription validity before enabling operations.

- Device Operation:

  - Once connected, LED turns Green (Configured).

  - Knob adjusts temperature threshold; color transitions indicate status:

    - White: Ready / Idle

    - Orange: Configuration mode

    - Green: Connected

    - Red: Threshold reached (Heater OFF)

Deliverables:

- Mobile app (Cross-platform React Native)

- API integration with existing backend

- OTA control screen for updates

- Add/Remove/Manage product functions

Phase 5: Testing & Quality Assurance

Objective:
Ensure the product is reliable, safe, and production-ready.

Tests:

- Functionality across multiple modules

- Continuous operation test (72 hours)

- Power-cycle and OTA stress tests

- Temperature hysteresis accuracy

- Safety and insulation checks on Power PCB

Deliverables:

- QA Report & Test Logs

- Final Production Firmware (Release Candidate)

Phase 6: Pilot Manufacturing & Documentation

Objective:
Finalize documentation for small-batch production and validation.

Deliverables:

- Final BOM(Bill of Materials), Assembly Drawings, and Test Fixtures

- User and Installer Manuals

- Pilot run of 10–20 units for real-field testing

- Production handover package

3. Technical Summary

| Component | Purpose |
| --- | --- |
| ESP32-C5 | Main control and Wi-Fi module with OTA |
| DS18B20 Sensor | Accurate temperature sensing |
| Relay / SSR | Heater control based on threshold |
| Knob (Potentiometer / Encoder) | Manual temperature setpoint |
| RGB LED Indicators | State visualization (Config / Connected / Threshold) |
| 5V DC Power Supply | From isolated Power PCB |
| Mobile App | Add/Manage device, Wi-Fi setup, OTA updates |
| Cloud Integration | Authentication & subscription verification |

4. Questions for Client Clarification

Before providing a final time and cost estimation, we require answers to the following:

A. Mobile App Requirements

- Do you prefer native development (Android/iOS separately) or cross-platform (React Native / Flutter)?

5. Estimated Development Phases & Duration (Tentative)

| Phase | Description | Duration |
| --- | --- | --- |
| Phase 1 | POC Development & Firmware v0 | 3 Weeks |
| Phase 2 | Multi-chip Testing | 1 Week |
| Phase 3 | PCB Design (Logic + Power) | 4 Weeks |
| Phase 4 | Prototype Assembly & Testing | 3 Weeks |
| Phase 5 | Mobile App Integration | 4 Weeks |
| Phase 6 | QA & Pilot Production | 2 Weeks |
| Total | Estimated Project Duration | 14–16 Weeks |

Final estimate to be confirmed post client clarification and approval of integration points.

6. Expected Outcomes

- A fully functional and scalable IoT Wax Heating Controller.

- Seamless Wi-Fi provisioning, temperature control, and OTA update functionality.

- Mobile app integrated with existing authentication and subscription systems.

- Dual-PCB hardware ready for pilot manufacturing.

- Comprehensive documentation, BOM, and test procedures for production handover.

7. Next Steps

- Client to review and answer Section 4 (Clarification Questions).

- Technical workshop (1–2 hours) to finalize data flow and mobile integration.

- Final estimation and milestone-based proposal submission.

- POC development kickoff upon approval.

Prepared By:
[Your Full Name]
[Your Company Name]
[Email ID]
[Phone Number]
[Website / Address]

Would you like me to format this into a clean 2-page PDF layout (with your company logo, sections highlighted, and ready to share with CGC or the client)?
I can prepare that next and attach it directly here.