Thanks, we got your point. We will create the POC based on the present design and will not add more LED like you expressed. The project will be divided into many steps/Phases, where as at this point in time we would like to create a complete POC that will include all the features, including a mobile working with minimal set of features. After this we will start working on creating the complete circuit schematic that is required for creating the scalable PCB.

Phase 1 — POC on Breadboard (ESP32-C5 based)

Goal: Prove all core functions on breadboard: WiFi provisioning (AP mode), unique AP SSID per unit, DS18B20 read, knob input, LED states, heater control via relay, OTA, basic app connection, auto-stop at threshold, LED Color transitions like it is working in the Current product.

Hours: 140 – 160
Weeks: 3 - 4

Tasks

- HW: Breadboard wiring, modules (ESP32-C5 devboard, DS18B20, rotary encoder / potentiometer, SSR/relay, test heater load).

- Firmware (iterative): WiFi AP provisioning, captive-portal-like flow or WiFi EasyConfig, unique AP names, state machine for LEDs, heater control PID/simple thermostat, DS18B20 driver, knob mapping, relay control, OTA (esp-idf ota or similar), persistent config storage.

- Mobile: Minimal demo app (or test script) to connect to device AP, send credentials and product unique code.

- Backend stub: Integration test harness to call subscription check (mock).

- Testing & demo: Single-unit functional test and demo to client.

Deliverables

- Working breadboard POC (demo video)

- Firmware V3 on ESP32-C5 with OTA support

- POC mobile screens to add product & config

Phase 2 — Multi-chip validation & firmware portability testing

Goal: Test the firmware with multiple chip/devboard samples (3–5), stress test OTA and heater cycles.

Hours: 40 – 60
Weeks: 1 – 2

Tasks

- Flash & test 5 different ESP32-C5 modules (different vendors/revisions).

- Run automated test scripts: power cycles, OTA from different servers, temperature boundary tests, knob hysteresis checks, relay lifecycles.

- Log and fix hardware/firmware variations.

Deliverables

- Multi-chip test report with issues & mitigations

- Firmware stable build for hardware designers

Phase 3 — Circuit Schematic (after POC validation)

Phase 4 – PCB Design & Manufacturing

Phase 5 – Integration & Testing