Thanks, we got your point. We will create the POC based on the present design and will not add more LED like you expressed. Please find the POC (breadboard + ESP32-C5), multi-chip testing, firmware features (heater control, DS18B20, knob, LEDs, relay, OTA), mobile app flow, backend integration/checks, split-PCB strategy (Logic + Power), PCB design & review, manufacturing readiness, and QA.

We have provided both the hour estimates (budgeting & planning) and calendar timelines (weeks), with understanding, deliverables and test plan.

1 — Project phases, deliverables & time estimate (hours & weeks)

Total estimated effort: ~560 – 760 hours (depending on refinement), delivered over 12–18 weeks with a 5-person team working in parallel where possible.

Below each phase I list hours (engineering hours) and an estimate in calendar weeks.

Phase 1 — POC on Breadboard (ESP32-C5 based)

Goal: Prove all core functions on breadboard: WiFi provisioning (AP mode), unique AP SSID per unit, DS18B20 read, knob input, LED states, heater control via relay, OTA, basic app connection, auto-stop at threshold, LED Color transitions like it is working in the Current product.

Hours: 120 – 160
Weeks: 3 - 4

Tasks

- HW: Breadboard wiring, modules (ESP32-C5 devboard, DS18B20, rotary encoder / potentiometer, SSR/relay, test heater load).

- Firmware (iterative): WiFi AP provisioning, captive-portal-like flow or WiFi EasyConfig, unique AP names, state machine for LEDs, heater control PID/simple thermostat, DS18B20 driver, knob mapping, relay control, OTA (esp-idf ota or similar), persistent config storage.

- Mobile: Minimal demo app (or test script) to connect to device AP, send credentials and product unique code.

- Backend stub: Integration test harness to call subscription check (mock).

- Testing & demo: Single-unit functional test and demo to client.

Deliverables

- Working breadboard POC (demo video)

- Firmware v0 on ESP32-C5 with OTA support

- POC mobile screens to add product & config

Phase 2 — Multi-chip validation & firmware portability testing

Goal: Test the firmware with multiple chip/devboard samples (3–5), stress test OTA and heater cycles.

Hours: 60 – 90
Weeks: 1 – 2

Tasks

- Flash & test 5 different ESP32-C5 modules (different vendors/revisions).

- Run automated test scripts: power cycles, OTA from different servers, temperature boundary tests, knob hysteresis checks, relay lifecycles.

- Log and fix hardware/firmware variations.

Deliverables

- Multi-chip test report with issues & mitigations

- Firmware stable build for hardware designers

Phase 3 — Hardware design: Schematics & Proto PCB (Logic & Power PCBs)

Goal: Create production-grade split-PCB design ready for prototype manufacturing.

Hours: 120 – 170
Weeks: 3 – 4 (parallel with Phase 2’s tail)

Tasks (Logic PCB)

- Schematic: ESP32-C5 module footprint, 5V regulator (if needed), DS18B20 connector, knob ADC path, RGB LED driver (MOSFET or LED driver IC), relay driver opto or MOSFET, debug UART, programming header, microSD if required.

- PCB layout: thermal vias for hot components, copper pours, mounting holes aligned to enclosure.

- EMI considerations, ESD protection on external connectors.

- BOM & part selection (automotive-rated components where needed).

Tasks (Power PCB)

- Schematic: AC input, input EMI, surge protection (MOV/TVS), high-voltage relay/SSR driver (if needed), AC→5V DC-DC (automotive-grade if intended for vehicles) or SMPS module, isolation clearances, fuses, inrush limiter.

- Safety spacing and creepage design following IEC for mains.

- Thermal design & layout, connector selection, BOM.

Deliverables

- Gerbers & manufacturing package for small-run PCBs (2–5 each)

- BOM & assembly drawing

Phase 4 — Prototype assembly, bring-up & firmware port to PCB

Hours: 70 – 110
Weeks: 2 – 3

Tasks

- Receive PCB prototypes, assemble (in-house or contract assembler).

- Firmware port & hardware bring-up: ADC cal, LED drivers, DS18B20 on board, relay control, OTA from PCB.

- Power PCB integration and safety checks (no-load, small-load test, then heater load test).

- Minor hardware revisions if needed (1 revision included).

Deliverables

- 2–5 assembled prototypes (Logic + Power) tested

- Hardware bring-up report & revised schematics if changes needed

Phase 5 — Mobile App (Production-grade) & Backend Integration

Hours: 120 – 160
Weeks: 3 – 4 (can run partially in parallel with Phase 4)

Tasks

- Full mobile app flows: Login/Signup (via client auth), Add product (scan QR / enter unique ID), provisioning flow (connect device AP → push WiFi credentials), subscription check API, product management screen, start/stop features, OTA trigger screen.

- Implement secure token flow with client backend (use provided API).

- Push notifications for alerts (optional — add hours if required).

- OTA management integration (optional server + auth).

- QA: integration testing with prototypes.

Deliverables

- iOS/Android (or cross-platform) app ready for UAT

- API integration doc & sample calls

Phase 6 — QA, Reliability & Pre-production Validation

Hours: 60 – 90
Weeks: 2

Tasks

- Functional test matrix (all features), endurance/soak testing (72 hrs continuous run on 3 units), OTA reliability (10 cycles), power-failure recovery & file-safe behaviour, knob hysteresis & setpoint accuracy, LED state correctness.

- Safety check for Power PCB at low & nominal loads, temperature rise measurements.

- Bug fixing & retests.

Deliverables

- QA test report, list of bugs fixed, release candidate firmware

Phase 7 — Documentation, Production Handoff & Small Pilot run

Hours: 50 – 70
Weeks: 1 – 2

Tasks

- Final BOM, assembly drawings, firmware build & toolchain, test fixtures for manufacturing, QA checklist for assembly, packaging notes.

- Pilot manufacturing: build 20–50 units (optional, manufacturing cost separate).

Deliverables

- Production package for manufacturer

- Pilot run units & test results

3 — Summary timeline (weeks) — typical parallel flow

- Weeks 0–0.5: Discovery & client Qs

- Weeks 1–3: POC breadboard & firmware v0

- Weeks 2–4: Multi-chip testing & early schematic work (parallel)

- Weeks 4–7: PCB schematic & layout, BOM, order prototypes

- Weeks 6–9: Prototype assembly & bring-up; initial app alpha

- Weeks 8–11: App production & backend integration; firmware hardening

- Weeks 10–13: QA, reliability, pilot run & documentation
Total: ~12–14 weeks (tight) — allowance 14–18 weeks for additional revisions / procurement delays.

4 — Rough effort totals (recap)

- Minimum engineering hours: ~560 hours

- Comfortable estimate: ~650 – 760 hours (includes buffer for re-spins and client feedback)

5 — Risks & mitigation

- Incomplete backend/API access — Mitigation: Require mock APIs or test endpoints early in Phase 0.

- ESP32-C5 module variations — Mitigation: Multi-chip testing in Phase 2, lock vendor part for production.

- Mains safety & layout mistakes — Mitigation: Use experienced HW engineer, follow creepage/clearance guidelines, optionally third-party review.

- OTA failures — Mitigation: Implement rollback partition scheme and verify many cycles during QA.

- Component lead times — Mitigation: Choose alternative components and order early.

6 — Deliverables (per milestone)

- POC demo & report (video + firmware)

- Multi-chip test report

- Schematics, PCB layouts, BOM (for both boards)

- Prototype units (2–5) + bring-up report

- Mobile app (builds + source) + API integration doc

- QA/Soak test report & release candidate firmware

- Production handoff package (Gerbers, BOM, assembly notes, test fixtures)